## Read first
Windows人工验收记录：现有证据整理
这是什么 | 你在Windows里实际点击功能并记下结果；不是再运行pytest。
本次已完成 | 依据原截图、实际PDF和JSON整理15项：8项已有部分证据，7项尚无完整操作记录。
状态含义 | Partially evidenced不是完整Pass；Not recorded不是Fail。508项自动测试的通过结果另行保留。
如何补齐 | 按Cases里的中文操作执行；如实填写执行日期、实际结果和证据；全部预期条件满足后才选Pass。
真实记录 | 日期/测试者/显示缩放不从截图文件名猜填；已有的Review date是资料核对日期。
保护原文件 | 缺失文件与取消覆盖只用自己的真实副本/临时导出文件，不移动主权重或删除原图。
不用重复 | 主要截图已齐，Cancelling瞬时图不要求重截；测试者可用文字/日志记录操作结果。
显示缩放 | 只报告实际测试的比例。未试的125%/150%/200%条件保持未测试，不推定全覆盖。

## Cases
Case | 中文操作 | Expected | Observed evidence | Current status | Evidence file | Still to check | Execution date | Tester | Actual conditions / result | Final outcome
W01 | 启动软件；还原为普通窗口；检查Run Inference可见；关闭再启动，观察窗口恢复。 | Normal window fits current available screen and retains usable actions | No complete execution record supplied for this case. | Not recorded |  | 启动软件；还原为普通窗口；检查Run Inference可见；关闭再启动，观察窗口恢复。
W02 | 依次最大化→还原→拖动缩小→最大化→还原；记录各次能否正常操作。 | Native states and normal geometry behave correctly without forced fullscreen | No complete execution record supplied for this case. | Not recorded |  | 依次最大化→还原→拖动缩小→最大化→还原；记录各次能否正常操作。
W03 | 打开原图对照；把窗口贴靠半屏；再恢复宽窗口；检查上下/左右布局自动切换与图像对齐。 | Vertical/horizontal adaptation works without Reset; views remain aligned | No complete execution record supplied for this case. | Not recorded |  | 打开原图对照；把窗口贴靠半屏；再恢复宽窗口；检查上下/左右布局自动切换与图像对齐。
W04 | 恢复49块结果；打开网格与编号；依次Fit、1:1、放大、缩小、调整窗口；查看第49块坐标。 | Complete aligned 7 × 7 grid; 480/464-pixel edge dimensions recorded | 49 numbered512-pixel tiles and paired Fit views are visible. | Partially evidenced | F4.3(b).png; F4.3(c).png | Record1:1/zoom/resize transitions and inspect tile49 actual edge coordinates; screenshots do not show the full sequence.
W05 | 分别点击勾选框、文字和内边距；按Tab/Space；每次应只切换一次，键盘焦点应可辨认。 | One transition per click; mouse/keyboard focus styles appropriate | No complete execution record supplied for this case. | Not recorded |  | 分别点击勾选框、文字和内边距；按Tab/Space；每次应只切换一次，键盘焦点应可辨认。
W06 | 打开History的两个日期日历；查看英文月份/星期；选择日期并核对筛选。 | English month/weekdays; correct selected dates and filtering | No complete execution record supplied for this case. | Not recorded |  | 打开History的两个日期日历；查看英文月份/星期；选择日期并核对筛选。
W07 | 先记下历史记录数；恢复一条记录应不新增；改当前设置后对该记录Re-run，核对记录参数。 | Recorded model/mode/parameters retained; restore itself does not rerun | History includes both modes; completed recorded Re-run83 retains512/49 while current defaults show256/196. | Partially evidenced | F4.5(a).png; F4_5_Rerun_completed_83.png; F4_5_Rerun_parameters_83.png | Record before/after history count for restoration alone and confirm recorded model/task under changed current defaults.
W08 | 启动真实分块工作后Cancel；核对历史无半成品；另一次运行中关闭窗口，记录清理与退出结果。 | Safe acknowledgement/cleanup; no partial completed record | Real operation progresses228/400; cancellation is acknowledged and displayed record79 is retained. | Partially evidenced | F4.9(a).png; F4.9(c).png | Record database/history outcome and close-while-busy cleanup; transient Cancelling screenshot is not required.
W09 | 记录实际显示缩放；打开Settings逐页滚到底并最大化/还原；检查内容、按钮和图例可访问。 | All content reachable, no artificial trailing height or clipped controls | No complete execution record supplied for this case. | Not recorded |  | 记录实际显示缩放；打开Settings逐页滚到底并最大化/还原；检查内容、按钮和图例可访问。
W10 | 打开已导出PDF和PNG；核对同一记录的模型/任务/参数/统计；检查配套JSON和文件可读性。 | Correct task/model/statistics; files readable; no unwanted identifying data | Actual two-page PDF opens; supplied JSON agrees with dimensions and all nine pixel counts. File listing showsPNG. | Partially evidenced | F4.6(a).png; F4.6(b).png; zypath_report_20261030_144310.pdf; zypath_result_20261030_144239.png.json | Open the actualPNG and record its readability and identity. Only its listing was supplied.
W11 | Models分别保存/恢复每任务默认；用不相容任务的可信权重或不存在路径核对错误，不创建假模型文件。 | Clear invalid/missing-file handling and task independence | Test-model segmentation default is saved and built-in default restored; classifier default remains displayed. | Partially evidenced | F4.9(d).png; F4.9(e).png | Check missing/incompatible-path messages and unchanged saved defaults. Test-model settings do not measure predictive accuracy.
W12 | 只用真实文件的副本建立测试记录；临时重命名副本；尝试恢复/Re-run，应提示缺失且不静默换模型；再恢复副本名。 | Actionable missing-file errors; no silent model substitution | No complete execution record supplied for this case. | Not recorded |  | 只用真实文件的副本建立测试记录；临时重命名副本；尝试恢复/Re-run，应提示缺失且不静默换模型；再恢复副本名。
W13 | 恢复旧512记录；将偏好改256后普通Run；再Recorded Re-run；最后再普通Run；分别核对512/256使用规则。 | Current Run geometry/backend match Preferences; Re-run retains its record; ordinary Run after rerun again uses current preferences | Ordinary Run77 uses256/196; recorded Re-run83 uses512/49 despite current256/196 defaults. | Partially evidenced | F4.5(d).png; F4_5_Rerun_completed_83.png; F4_5_Rerun_parameters_83.png | Complete and record the full old-record→changed-preference→Re-run→ordinary-Run sequence, including final new-run parameters.
W14 | 点击编号与表格行，核对原裁块；Square后单独改高度；Clear view和Clear Selection后核对历史/文件仍保留。 | IDs/boxes/crop preview agree; Square copies once; clear operations preserve saved history/source files | Number31 matches the crop preview, rectangle[1024,2048,1536,2560], NORM and59.47% confidence. | Partially evidenced | F4.3(c).png | Demonstrate Square copying once, independent width/height editing, Clear view and zero-row selection without removing saved data.
W15 | 同一结果导出两种PDF质量；核对数字一致；用专门临时文件测试取消覆盖，核对原文件未变。 | Quality and original dimensions are accurately labelled; numeric data agree; cancellation/failed export preserve the previous destination | Standard PDF is875021bytes with quality/source dimensions and recorded numeric data. | Partially evidenced | zypath_report_20261030_144310.pdf; F4.6(b).png | Compare both quality modes and numeric rows; cancel an overwrite of a disposable destination and check its prior hash is retained.

## Summary
Measure | Value
Reviewed cases | 15
Partially evidenced | 8
Not recorded | 7
New formal Pass assigned by this review | 0
New Fail assigned by this review | 0
Existing automatic regression | 508 passed,0 failed/errors/skipped; source3a935ef
User feedback | Not collected; this is not UAT